## Sponsor Inputs
# | High level ideas / Features
1 | Create Account
2 | View Restaurants
3 | Search Restaurants
4 | View Menu
5 | Add to Cart
6 | Purchase
7 | Restaurant views order
8 | Restaurant marks order as delivered
Notes:
1 | The above points were listed as draft ideas by the project sponsor.
2 | The project sponsor mentioned that he wants to compete against Talabat.
3 | As a sponsor, I am planning to compete against Talabat.
4 | This is a view only file, you can make a copy then edit in the copy.
5 | You can find a tab named Product Backlog Template, please feel free to use it when creating your product backlog.

## Product Backlog Template
# | Epic | User Story | Priority | Ready to be planned | Planned Sprint | Status
As a < type of user >, I want < some goal > so that < some reason >
| Create Account | As a user, I want to create an account so that I can safely add my data and have the authority to order | high | yes | 1
|  | As a restaurant, I want to create an account so I can have virtual restaurants and show the users my menu. | high | yes | 1
| View Restaurants | As a user, I want to view restaurants so I can order from different, nearer, or new restaurants. | high | yes | 1
| Search Restaurants | As a user, I want to search for restaurants so I can find the one I want, so I won't scroll down to find it. | medium | yes | 2
| View Menu | As a user, I want to view the menu so I can choose the items I can order. | high | yes | 1
| Add to Cart | As a user, I want to add this item to my cart so I can choose the amount I need from this item. | medium | yes | 2
| Purchase | As a user, I want to make a purchase so I can choose the payment method. So I can find the total bill | high | yes | 1
| Restaurant views order | As a restaurant, I want to view the order so I can prepare it and deliver it. | high | yes | 1
| Restaurant marks order as delivered | As a restaurant, I want to mark an order as delivered so I can remove it from my order list. | medium | yes | 2
|  | As a user, I want the restaurant to mark the order as delivered so I can see it in history or so I can contact the delivery man. | medium | yes | 2